## Form A
| ARCHITECT'S |  |  | A
Proposed Change Order Form
TO: Contractor
Please prepare a CONTRACTOR'S PROPOSED CHANGE ORDER FORM B |  |  | TFC PROJECT NO.
on the following proposed change: (Additional sealed documents necessary
to completely describe the change identified below are attached.)
PROPOSED CHANGE ORDER NO.
Work shall not commence until an executed Change Order is issued through the EPMCS with the exception ULCOs issued under UGC 11.9.
DATE
This Proposed Change Order was initiated | Your early response is solicited
by | by
Signature
Architect / Engineer
ROUTING INFORMATION
1. Architect / Engineer prepare Proposed Change Order (PCO) in Impact and assign PCO number. Prepare and upload form "A", along with any attachments and transmit to Contractor via Impact. |  | 4. TFC staff review all documents, fill in amounts on CHANGE ORDER form, assign CHANGE ORDER NUMBER, and endorse. Transmit to Using Agency via email/Impact.
5. Using Agency review all documents and endorse CHANGE ORDER form. Transmit to TFC via Impact.
2. Contractor prepare Form "B." Respond to PCO in Impact, upload Form "B" and transmit to Architect / Engineer.
6. TFC final Approval. Transmit copies of all documents to all parties via Impact.
3. Architect / Engineer review Form "B" and prepare Form "C". Upload Form "C" and transmit to TFC via Impact.

## Form B
|  | CONTRACTOR'S |  |  | B
Proposed Change Order Form
TO: Architect / Engineer
The following is a detailed cost breakdown, including both materials |  |  |  | TFC PROJECT NO.
and labor for all additions to and/or deductions from the contract
sum if the change described on form A is accepted. (Additional data
necessary to support itemized figures is attached and identified below.) |  |  |  | PROPOSED CHANGE ORDER NO.
DATE
Is this PCO a ULCO?
Total Addition / Deduction (circle one) to CONTRACT SUM if accepted: |  |  | $
Request is made for addition of _______ CALENDAR DAYS to the contract period.
The above proposal is submitted for your consideration. The undersigned contractor understands and agrees
that this proposal is not considered finalized until an executed Change Order is issued through the EPMCS.
Work will not commence until the executed Change Order is issued with the exception of ULCOs issued under UGC 11.9.
Authorized Signature
Name of Contracting Firm

## Form C
|  | ARCHITECT'S |  |  | C
Proposed Change Order Form
TO: Texas Facilities Commission
AND:
| PM/ODR |  |  | TFC PROJECT
The Proposed Change Order Documents are presented for your consideration
and approval. The Contractor's Form "B" has been reviewed |  |  |  | PROPOSED CHANGE ORDER NO.
and it is recommended for approval by the undersigned. Acceptance of this
change is recommended for the following REASON and JUSTIFICATION.
DATE
REASON:
JUSTIFICATION:
Work shall not commence until an executed Change Order is issued through the EPMCS with the exception ULCOs issued under UGC 11.9.
Respectfully submitted
by
Signature
Architect / Engineer